## 1. Project Overview
Section | Details
Project Name | Oncology Care Management EHR Platform
Project Type | SaaS — Hospital & Patient-Facing EHR System for Oncology
Prepared For | [Client / Hospital Name]
Prepared By | TPAI Engineering Team
Date | March 2026
Version | 2.0 — Infrastructure-First + AI Integration
VISION
Purpose | Build a comprehensive, role-based oncology EHR platform that hospitals can deploy to manage cancer patients through their entire treatment journey — from diagnosis through chemotherapy cycles, emergency events, medication management, and ongoing benchmarking. Includes AI-powered document analysis and treatment recommendations.
Patient Value | Patients get a personal portal to track remaining chemo sessions, view treatment progress, receive notifications for missed appointments, and stay connected with their care team.
Hospital Value | Hospitals get a powerful dashboard with real-time benchmarks, compliance tracking, ER visit monitoring, role-based workflows for doctors/nurses/chemists, automated notification systems, and AI-powered report analysis.
AI Value | AI analyzes uploaded medical reports (PDF/scanned documents) using OCR + LLM to extract structured data, auto-create oncology records, calculate AJCC staging, and generate treatment roadmaps based on NCCN guidelines.
TECH STACK
Frontend | React 18 + TypeScript + Vite + Tailwind CSS / Ant Design
Backend | NestJS + TypeScript + TypeORM + PostgreSQL
AI/ML | Groq API (Llama 3.3 70B) + Tesseract OCR + pdfplumber + pdf2image
Infrastructure | Docker + Docker Compose + GitHub Actions + Nginx
CANCER TYPES COVERED
1 | Breast Cancer — Chemotherapy protocols, hormone therapy tracking, HER2 status monitoring
2 | Prostate Cancer — PSA benchmarking, radiation + chemo cycles, hormone therapy tracking
3 | Lung Cancer — Staging (SCLC/NSCLC), immunotherapy + chemo tracking, PFT benchmarks
4 | Colorectal Cancer — CEA marker tracking, surgical + chemo timelines, colonoscopy scheduling
KEY CAPABILITIES
AI Report Analysis | Upload medical reports (PDF/images) → OCR text extraction → LLM-powered data extraction → Auto-create oncology records
AI Treatment Roadmap | AI generates treatment recommendations (surgery, chemo, radiation, immunotherapy) based on cancer type, stage, biomarkers & NCCN guidelines
AJCC Staging | Deterministic AJCC 8th Edition cancer staging engine for Breast, Prostate, Lung, Colorectal cancers
Chemo Tracking | Track total cycles prescribed vs completed, next session dates, missed sessions with reasons
Smart Notifications | Automated alerts via Email/SMS/Push to patient, emergency contact, and care team
Benchmarking | Tumor marker trends (up/down), treatment response rates, survival benchmarks per cancer type
ER Monitoring | Track emergency room visits, extra medications administered, unplanned hospitalizations
Role-Based Access | SuperAdmin, Hospital Admin, Doctor, Nurse, Chemist/Pharmacist, Patient — each with specific permissions
Reporting | Exportable reports for compliance, insurance, and clinical audits

## 2. Phase-Wise Plan
Phase | Sprint | Duration | Module / Deliverable | Key Tasks | Owner | Status | Priority
Phase 1: Basic Infrastructure | Sprint 1 | Week 1–2 | Environment & Configuration Setup | • Create .env files (Dev/Staging/Prod) with all config variables • Configure database connection with environment variables • Setup TypeORM migrations (disable synchronize:true) • Generate initial migration from existing entities • Configure CORS properly for all environments • Setup logging (Winston/Pino logger) • Health check endpoint (/api/health) | DevOps + Backend Lead | Not Started | P0 — Critical
Phase 1: Basic Infrastructure | Sprint 1 | Week 1–2 | Docker & Containerization | • Dockerfile for NestJS backend (multi-stage build) • Dockerfile for React frontend • docker-compose.yml (backend + frontend + PostgreSQL + Redis) • docker-compose.dev.yml for local development • Volume mounts for hot-reload in dev • .dockerignore files • Docker health checks | DevOps | Not Started | P0 — Critical
Phase 1: Basic Infrastructure | Sprint 1 | Week 1–2 | CI/CD Pipeline | • GitHub Actions workflow for backend (lint + test + build) • GitHub Actions workflow for frontend (lint + test + build) • Automated testing on PR • Docker image build & push to registry • Dev/Staging deployment automation • Branch protection rules • Environment secrets management | DevOps | Not Started | P0 — Critical
Phase 1: Basic Infrastructure | Sprint 2 | Week 3–4 | DTO Validation Layer (Backend) | • Create DTOs for ALL existing endpoints (currently using 'any' types) • Patient DTOs: CreatePatientDto, UpdatePatientDto, PatientQueryDto • Allergy DTOs: CreateAllergyDto, UpdateAllergyDto • Vitals DTOs: CreateVitalsDto, UpdateVitalsDto • Medication DTOs: CreateMedicationDto, UpdateMedicationDto • ChronicCondition DTOs: CreateChronicConditionDto, UpdateChronicConditionDto • Lifestyle/MedicalHistory DTOs • Oncology DTOs: CreateOncologyRecordDto, UpdateOncologyRecordDto • Treatment, FollowUp, Symptom, Payer DTOs • Auth DTOs: LoginDto, RefreshDto • Apply class-validator decorators (@IsString, @IsEmail, @IsOptional, etc.) • Swagger @ApiProperty decorators on all DTOs | Backend Team | Not Started | P0 — Critical
Phase 1: Basic Infrastructure | Sprint 2 | Week 3–4 | Error Handling & Response Standardization | • Global exception filter (HttpExceptionFilter) • Standardized API response format: { success, data, message, errors } • Custom exception classes (PatientNotFoundException, etc.) • Validation error formatting (field-level errors) • Database error handling (unique constraint, FK violations) • Request/Response logging interceptor • API versioning strategy (v1 prefix) | Backend Lead | Not Started | P0 — Critical
Phase 1: Basic Infrastructure | Sprint 2 | Week 3–4 | File Upload Infrastructure | • Multer configuration for file uploads in NestJS • File storage service (local disk + S3-compatible) • File type validation (PDF, PNG, JPG, JPEG, DICOM) • File size limits (configurable per type, e.g., 50MB for PDFs) • Secure file serving endpoint with auth • File cleanup service (orphaned files) • Media directory structure (/uploads/reports/, /uploads/documents/) | Backend Team | Not Started | P0 — Critical
Phase 2: Auth & RBAC | Sprint 3 | Week 5–6 | Enhanced Authentication | • Role-based access control (RBAC) with guards • Roles: SuperAdmin, Hospital Admin, Doctor, Nurse, Chemist, Patient • @Roles() decorator + RolesGuard • Register endpoint (POST /api/auth/register) • Forgot Password flow (email-based reset token) • Change Password endpoint • Session management & token blacklisting on logout • Refresh token rotation • Audit logging for ALL auth events (login, logout, failed attempts) • Rate limiting on auth endpoints (throttler) | Backend Lead | Not Started | P0 — Critical
Phase 2: Auth & RBAC | Sprint 3 | Week 5–6 | User Management Module | • User entity enhancement (role, hospital_id, profile fields) • SuperAdmin: CRUD for hospitals and admins • Hospital Admin: CRUD for doctors, nurses, chemists • Profile management for all roles • Role permission matrix implementation • User search & filtering • User activation/deactivation • Swagger docs for all user endpoints | Full Stack Team | Not Started | P0 — Critical
Phase 3: Core Patient & Oncology | Sprint 4 | Week 7–8 | Patient Module Hardening | • Apply DTOs to all existing patient endpoints • Patient demographics & medical history validation • Insurance & emergency contact management • Cancer diagnosis intake form • Patient search & advanced filtering (date ranges, cancer type, status) • Pagination with proper metadata (total, page, limit) • Patient photo upload • Soft-delete & restore functionality testing | Backend + Frontend | Not Started | P1 — High
Phase 3: Core Patient & Oncology | Sprint 5 | Week 9–10 | Breast Cancer Module | • Diagnosis details (ER/PR/HER2 status, tumor grade) • Chemotherapy protocol assignment (AC-T, TC, etc.) • Cycle tracking (prescribed vs completed) • Hormone therapy tracking • Tumor marker benchmarks (CA 15-3) • Treatment response assessment | Oncology Team | Not Started | P1 — High
Phase 3: Core Patient & Oncology | Sprint 6 | Week 11–12 | Prostate Cancer Module | • Diagnosis (Gleason score, PSA levels, staging) • Chemo protocol assignment (Docetaxel, Cabazitaxel) • PSA trend benchmarking (rising/falling) • Hormone/ADT therapy tracking • Radiation therapy integration • Treatment response metrics | Oncology Team | Not Started | P1 — High
Phase 3: Core Patient & Oncology | Sprint 7 | Week 13–14 | Lung Cancer Module | • Diagnosis (SCLC vs NSCLC, staging, mutations: EGFR, ALK, ROS1, PD-L1%) • Chemo protocol (Cisplatin/Carboplatin combos) • Immunotherapy tracking (Pembrolizumab, etc.) • PFT (Pulmonary Function Test) benchmarks • Tumor marker monitoring (CYFRA 21-1, NSE) • Treatment line tracking (1st, 2nd, 3rd line) | Oncology Team | Not Started | P1 — High
Phase 3: Core Patient & Oncology | Sprint 8 | Week 15–16 | Colorectal Cancer Module | • Diagnosis (staging, tumor location, MSI status) • Chemo protocol (FOLFOX, FOLFIRI, CAPOX) • CEA marker trend tracking • KRAS/NRAS/BRAF mutation tracking • Surgical timeline integration • Colonoscopy scheduling & follow-up • Treatment response (RECIST criteria) | Oncology Team | Not Started | P1 — High
Phase 4: AI Integration — OCR & Text Extraction | Sprint 9 | Week 17–18 | MedicalReport Entity & File Upload Pipeline | • Create MedicalReport entity (port from Django model) — Fields: file, document_type, extracted_text, extracted_data (JSONB), insights (JSONB), recommendations (JSONB), status, page_count, estimated_tokens, is_scanned, retry_count • Create ProcessingProgress entity (tracks document processing stages) • MedicalReport CRUD endpoints • File upload endpoint: POST /api/medical-reports/upload • Processing status endpoint: GET /api/medical-reports/:id/status • Insights endpoint: GET /api/medical-reports/:id/insights • Approve endpoint: POST /api/medical-reports/:id/approve • Retry endpoint: POST /api/medical-reports/:id/retry • DTOs + Swagger docs for all report endpoints | Backend Team | Not Started | P1 — High
Phase 4: AI Integration — OCR & Text Extraction | Sprint 9 | Week 17–18 | Text Extraction Service (OCR + PDF) | • Install & configure system dependencies (Tesseract, Poppler) • Port TextExtractionService from Django → NestJS service • PDF text extraction using pdfplumber (Node equivalent: pdf-parse or pdf.js) • Scanned PDF detection (< 50 chars = image-based) • Scanned PDF OCR: pdf-to-image conversion + Tesseract • Image OCR with preprocessing: grayscale → contrast → sharpen → upscale • Tesseract config: --oem 3 --psm 3 • OCR text cleanup: whitespace fixes, artifact removal (¦→I), medical term corrections (Gleason, Adenocarcinoma, Pathology Report) • Smart routing: try digital extraction first, fallback to OCR • Support formats: PDF, PNG, JPG, JPEG, TIFF • Unit tests for extraction service | AI/Backend Team | Not Started | P1 — High
Phase 4: AI Integration — LLM Analysis | Sprint 10 | Week 19–20 | AI Analysis Service (Groq/LLM Integration) | • Install Groq SDK for Node.js (groq-sdk npm package) • Configure Groq API: GROQ_API_KEY, model (llama-3.3-70b-versatile), timeout (30s), max_tokens (1500), temperature (0.1) • Port AIAnalysisService from Django → NestJS: — Direct mode: full text → single Groq API call → parse JSON response — Chunked mode: text > 6000 tokens → split into overlapping chunks → per-chunk API call → merge results • Document-type-specific LLM prompts: — Generic medical report extraction prompt — Lab report prompt (test names, values, units, reference ranges) — Radiology/imaging prompt (findings, measurements, severity) — Prescription prompt (drug names, dosages, frequencies) — Clinical note prompt (diagnoses, procedures, medications) — Pathology report prompt (FULL oncology schema: cancer type, TNM staging, histology, biomarkers, ER/PR/HER2, Gleason, EGFR, ALK, PD-L1, KRAS, BRAF, MSI/MMR, IHC, specimen info) • JSON response parsing with validation • Error handling: API timeouts, rate limits, malformed responses • Retry logic with exponential backoff • Unit + integration tests | AI/Backend Team | Not Started | P1 — High
Phase 4: AI Integration — LLM Analysis | Sprint 10 | Week 19–20 | Document Chunking Service | • Port ChunkingService from Django → NestJS • Token estimation (character-count / 4 approximation) • Text splitting: 6000 token chunks with 200-token overlap • Smart chunk boundaries (avoid splitting mid-sentence) • Result merging across chunks: — Oncology data merging (first non-null wins for scalar fields) — Pathology info merging — Vitals, lab results, medications deduplication — Allergies, diagnoses, insights list union — Biomarker/IHC dictionary merging • Unit tests for chunking & merging logic | AI/Backend Team | Not Started | P1 — High
Phase 4: AI Integration — Post-Processing | Sprint 11 | Week 21–22 | Abnormal Lab Detection & Report Type Classification | • Port abnormal lab detection logic to NestJS — Parse reference ranges from AI-extracted lab results — Flag values outside normal ranges (is_abnormal boolean) — Handle edge cases: '<', '>', ranges like '10-20' • Port report type auto-detection (NLP keyword matching) — Keyword-based classification: pathology, ultrasound, X-ray, CT scan, MRI, PET scan, mammography, radiology, lab report — Minimum 2 keyword matches for pathology (OCR robustness) — No LLM API call — pure regex/keyword matching • Unit tests for both services | AI/Backend Team | Not Started | P1 — High
Phase 4: AI Integration — AJCC Staging | Sprint 11 | Week 21–22 | AJCC 8th Edition Staging Engine | • Port AJCCStagingEngine from Django → NestJS (deterministic, no AI) • Breast cancer staging: — Anatomic staging (T + N + M) — Prognostic staging (T + N + M + Grade + ER/PR/HER2) — Molecular subtype classification (Luminal A/B, HER2+, Triple-negative) • Prostate cancer staging: — NCCN Risk Groups (T stage + PSA + Gleason primary/secondary score) • Lung cancer staging (NSCLC): — TNM stage groups mapping • Colorectal cancer staging: — TNM stage groups mapping • Stage-specific treatment recommendations: — Stage IV → URGENT systemic therapy, palliative care, molecular testing — Stage III → Tumor board, neoadjuvant therapy, staging imaging — Stage II → Surgical consultation, adjuvant therapy — Cancer-specific: BRCA testing (breast), active surveillance (prostate), smoking cessation (lung), CEA monitoring (colorectal) • Comprehensive unit tests for all cancer type staging | AI/Backend Team | Not Started | P1 — High
Phase 4: AI Integration — Auto-Population | Sprint 12 | Week 23–24 | Data Population Service (AI → Patient Records) | • Port DataPopulationService from Django → NestJS • Auto-populate patient records from AI-extracted data: — Vitals records (data_source='automated', source_report FK) — Medication records (data_source='automated') — Allergy records (data_source='automated') — ChronicCondition records (data_source='automated') • Report approval workflow: — Admin reviews AI analysis → clicks Approve — Triggers DataPopulationService.populatePatientRecords() — Sets report status to 'approved' • Data source tracking on all auto-created records • Duplicate detection (don't create duplicate allergies/meds) | Backend Team | Not Started | P1 — High
Phase 4: AI Integration — Auto-Population | Sprint 12 | Week 23–24 | Auto Oncology Record Creation from Pathology Reports | • Port auto_create_oncology_record from Django → NestJS • Trigger: pathology report with recognized cancer_type in extracted_data • Auto-create OncologyRecord with: — Mapped cancer type (breast → breast_cancer, etc.) — TNM staging from AI extraction — Histology, grade, tumor size, biomarkers — confirmed_by = 'ai', diagnosis_confirmed = false — AI confidence score • Link PathologyReport FK to OncologyRecord • POST /api/oncology-records/create-from-report endpoint | Backend Team | Not Started | P1 — High
Phase 4: AI Integration — Treatment Roadmap | Sprint 12 | Week 23–24 | AI Treatment Roadmap Generation | • Port treatment roadmap generation from Django → NestJS • Second Groq API call after oncology record creation • Prompt includes: cancer type, AJCC stage, histology, grade, tumor size, lymph node status, biomarkers, AI analysis insights • LLM generates NCCN-guideline-based recommendations: — recommended_surgery (specific procedure suggestions) — recommended_chemotherapy (specific regimen suggestions) — recommended_radiation (type + dosing) — recommended_immunotherapy (specific agents) — recommended_targeted_therapy (mutation-specific agents) — treatment_intent (curative/palliative/adjuvant/neoadjuvant) — urgency_level (emergent/urgent/semi_urgent/routine) • Save roadmap to OncologyRecord fields • roadmap_generated_at timestamp • GET /api/oncology-records/:id/treatment-roadmap endpoint • Integration tests with mock Groq responses | AI/Backend Team | Not Started | P1 — High
Phase 5: AI Processing Pipeline | Sprint 13 | Week 25–26 | Document Processing Pipeline (End-to-End) | • Port DocumentProcessingService orchestrator to NestJS • Full processing pipeline: Step 1: File upload → validate → store Step 2: TextExtractionService.extractText() → PDF? → pdfplumber/pdf-parse extraction → Scanned PDF? → pdf2image + Tesseract OCR → Image? → preprocessing + Tesseract OCR → Save extracted_text, status='text_extracted' Step 3: AIAnalysisService.analyzeMedicalText() → Token estimation → direct or chunked mode → Post-processing: abnormal lab detection, AJCC staging → Save extracted_data, insights, recommendations → status='analysis_complete' Step 3b (if pathology): Auto-create OncologyRecord → Generate treatment roadmap (2nd Groq API call) Step 4: Await admin approval Step 5: DataPopulationService.populatePatientRecords() • Background processing with BullMQ (Redis-backed queue) • Configurable concurrency & retry policies | AI/Backend Team | Not Started | P1 — High
Phase 5: AI Processing Pipeline | Sprint 13 | Week 25–26 | Processing Progress Tracking (Real-Time) | • ProcessingProgress entity tracking stages: initializing → extracting_text → running_ocr → chunking → ai_analysis → merging_results → staging → populating → complete/failed • Current step / total steps / percentage tracking • Current page / current chunk granular progress • WebSocket or SSE for real-time progress updates to frontend • GET /api/medical-reports/:id/progress endpoint • Progress bar component in React frontend • Error recovery: resume from last successful step | Full Stack Team | Not Started | P2 — Medium
Phase 5: AI Processing Pipeline | Sprint 14 | Week 27–28 | AI Quality & Confidence Scoring | • Document complexity analyzer (port from Django) — Estimate processing difficulty based on page count, OCR quality, document type, text density • AI confidence scoring per extraction field • Low-confidence flagging for human review • A/B comparison: AI-extracted vs manually-entered data • AI extraction accuracy dashboard for admins • Bulk document processing (batch upload) • Processing queue management (pause, cancel, re-priority) | AI/Backend Team | Not Started | P2 — Medium
Phase 6: Chemo & Treatment Engine | Sprint 15 | Week 29–30 | Chemotherapy Scheduling Engine | • Calendar-based chemo cycle scheduling • Auto-calculate next session dates based on protocol • Missed session detection & flagging • Pre-chemo checklist (blood work, vitals) • Cycle completion tracking (X of Y done) • Treatment delay documentation • AI-suggested optimal scheduling based on patient data | Backend Lead | Not Started | P1 — High
Phase 6: Chemo & Treatment Engine | Sprint 15 | Week 29–30 | Medication & Prescription Management | • Chemo drug catalog (per cancer type) • Dosage calculation (BSA-based) • Supportive medication tracking (anti-nausea, etc.) • Extra/emergency medication logging • Drug interaction alerts • Chemist/Pharmacist verification workflow • AI-extracted medications cross-reference with prescriptions | Backend + Chemist Flow | Not Started | P1 — High
Phase 7: Notifications & Alerts | Sprint 16 | Week 31–32 | Notification System | • Email notifications (SendGrid/AWS SES) • SMS notifications (Twilio) • Push notifications (Firebase) • Notification templates per event type • Notification preferences per user • Notification history & read tracking • AI processing completion notifications | Backend Team | Not Started | P1 — High
Phase 7: Notifications & Alerts | Sprint 16 | Week 31–32 | Alert Rules Engine | • Missed chemo session → Notify patient + emergency contact • Doctor unavailable → Notify patient + assign backup • Abnormal benchmark → Alert care team • ER visit logged → Notify oncologist • Treatment milestone → Notify patient • Custom alert rules per hospital • AI-detected critical findings → Urgent alert to oncologist | Backend Team | Not Started | P1 — High
Phase 8: Benchmarks & Analytics | Sprint 17 | Week 33–34 | Benchmarking Dashboard | • Tumor marker trend charts (up/down arrows) • Treatment response rates per cancer type • Chemo completion rates • Side-effect frequency tracking • Comparative benchmarks (hospital vs national) • Patient outcome scoring • AI-extracted lab result trends over time | Frontend + Data | Not Started | P1 — High
Phase 8: Benchmarks & Analytics | Sprint 17 | Week 33–34 | ER & Emergency Tracking | • Emergency room visit logging • Reason categorization (fever, pain, reaction, etc.) • Extra medications administered in ER • Unplanned hospitalization tracking • ER visit trends per patient/cancer type • Cost impact analysis | Full Stack Team | Not Started | P1 — High
Phase 8: Benchmarks & Analytics | Sprint 18 | Week 35–36 | Patient-Facing Portal | • Treatment journey timeline view • Remaining chemo sessions counter • Next appointment details • Medication list & schedule • Doctor/nurse contact info • Symptom self-reporting • AI-generated treatment summary (plain language) • Document access (reports, prescriptions) • Appointment reminders (email + SMS + push) | Frontend Team | Not Started | P1 — High
Phase 9: Reporting & Compliance | Sprint 19 | Week 37–38 | Reports & Exports | • Patient treatment summary reports (PDF) • Hospital-wide oncology analytics • Insurance/billing report generation • Compliance audit reports • AI analysis audit trail (who approved, what was changed) • Custom report builder • Scheduled report delivery (email) | Full Stack Team | Not Started | P2 — Medium
Phase 10: Testing & Deployment | Sprint 20–21 | Week 39–42 | QA, UAT & Deployment | • Unit & integration testing (>80% coverage) • End-to-end testing (Cypress/Playwright) • AI service testing (mock Groq responses, OCR test images) • Security audit & penetration testing • HIPAA compliance review • Performance & load testing • AI processing load testing (concurrent document uploads) • UAT with hospital staff • Production deployment • Documentation & training materials | QA + DevOps | Not Started | P0 — Critical

## 3. AI Features Detail
AI Feature | What It Does | Input | Output | Technology | Django Reference | NestJS Implementation Plan
DOCUMENT PROCESSING PIPELINE
PDF Text Extraction | Extracts text from born-digital PDFs (text is selectable in the PDF). Uses pdfplumber to directly read text layer. | PDF file (born-digital) | Plain text (extracted_text field on MedicalReport) | pdfplumber (Python) → pdf-parse or pdf.js (Node) | text_extraction_service.py Lines 260-285 | Create TextExtractionService in NestJS Use pdf-parse npm package Same logic: extract text per page, concatenate
Scanned PDF Detection | Detects if a PDF is image-based (scanned) by checking if first page has < 50 characters of extractable text. | PDF file | Boolean (is_scanned) | pdfplumber text length check | text_extraction_service.py Lines 55-70 | After pdf-parse extraction, check text.length < 50 If true → route to OCR pipeline
Scanned PDF OCR | Converts each PDF page to an image, then runs Tesseract OCR on each page. Handles multi-page scanned documents. | Scanned PDF file | Extracted text (per page, concatenated) | pdf2image + pytesseract + PIL → pdf-poppler/pdf2pic + node-tesseract-ocr + sharp (Node) | text_extraction_service.py Lines 105-175 | Use pdf-poppler or pdf2pic to convert PDF → images Use node-tesseract-ocr or tesseract.js for OCR Process page by page
Image OCR with Preprocessing | Advanced image preprocessing before OCR: convert to grayscale, enhance contrast (2.0x), sharpen, upscale small images. Then run Tesseract with optimized config. | Image file (PNG/JPG/JPEG/TIFF) | Extracted text (cleaned) | PIL (contrast/sharpen/resize) + pytesseract → sharp (Node) + tesseract.js | text_extraction_service.py Lines 290-345 | Use sharp for image preprocessing: - .grayscale() - .sharpen() - .resize() for small images Tesseract config: --oem 3 --psm 3
OCR Text Cleanup | Post-processes OCR output to fix common artifacts: whitespace normalization, pipe→I replacement, medical term corrections (Gleason, Adenocarcinoma), noise line removal. | Raw OCR text | Cleaned text | Regex (Python re) → Regex (Node.js) | text_extraction_service.py Lines 347-374 | Port regex patterns to Node.js Same cleanup rules: - Fix ¦→I - Fix spacing - Medical term corrections
AI ANALYSIS (LLM-POWERED)
Medical Report AI Analysis (Direct) | Sends full extracted text to Groq Llama 3.3 70B in a single API call. LLM extracts structured medical data and generates clinical insights + recommendations. | Extracted text (≤ 6000 tokens) + Document type | JSON: { vitals, lab_results, medications, allergies, diagnoses, insights, recommendations, oncology_data (if pathology) } | Groq API (llama-3.3-70b-versatile) temp=0.1, max_tokens=1500 JSON response format | ai_analysis_service.py Lines 52-167 | Use groq-sdk npm package Same API params: model, temp, max_tokens Same prompt structure per document type Parse JSON response with validation
Medical Report AI Analysis (Chunked) | For large documents (> 6000 tokens): splits text into overlapping chunks, sends each to Groq separately, then intelligently merges all results. | Extracted text (> 6000 tokens) + Document type | Merged JSON (same structure as direct) | ChunkingService + Groq API N API calls (one per chunk) | ai_analysis_service.py Lines 169-262 | Port chunking logic to NestJS 6000 token chunks, 200 overlap Merge: first-non-null for scalars, union for lists, merge for dicts
Document Type Auto-Detection | Rule-based NLP that classifies document type from text content using keyword matching. NO AI API call — pure regex. Detects: pathology, ultrasound, X-ray, CT, MRI, PET, mammography, radiology, lab report. | Extracted text (any document) | Document type classification string | Keyword matching + counting No LLM / No API call | ai_analysis_service.py Lines 310-370 | Port keyword dictionaries to NestJS Same logic: count keyword matches ≥2 matches for pathology (OCR robustness)
Pathology Report Deep Extraction | Specialized LLM prompt for pathology reports that extracts the FULL oncology schema: cancer type, TNM staging, histology, biomarkers (ER/PR/HER2, Gleason, EGFR, ALK, PD-L1, KRAS, BRAF, MSI/MMR), specimen info, ICD codes, immunohistochemistry. | Pathology report text + pathology-specific prompt | JSON: { oncology_data: { cancer_type, tnm_staging, histology, grade, tumor_size, biomarkers, lymph_nodes, margins, specimen_info, icd_codes, ihc_results }, pathology_info: { ... } } | Groq API with specialized pathology prompt (215 lines) | ai_analysis_service.py Lines 855-1070 | Port the 215-line pathology prompt JSON schema must match exactly This is the most complex prompt — test with real pathology reports
Abnormal Lab Detection | Post-processes AI-extracted lab results. Parses reference ranges and flags values outside normal (is_abnormal). Handles edge cases: '<', '>', ranges '10-20'. Deterministic — NOT an AI call. | AI-extracted lab results array | Lab results with is_abnormal boolean | Deterministic parsing No LLM / No API call | ai_analysis_service.py Lines 264-291 | Port parsing logic to TypeScript Handle: numeric, ranges, '<', '>' Set is_abnormal on each result
STAGING & RECOMMENDATIONS
AJCC 8th Edition Staging (Breast) | Deterministic staging engine for breast cancer. Anatomic staging (T+N+M) and Prognostic staging (T+N+M+Grade+ER/PR/HER2). Classifies molecular subtypes: Luminal A/B, HER2+, Triple-negative. | TNM values, grade, ER/PR/HER2 status | AJCC stage (IA, IB, IIA, IIB, IIIA, IIIB, IIIC, IV) + Molecular subtype + Prognostic stage | Lookup tables No LLM / No API call | ajcc_staging_engine.py Lines 85-260 | Port staging lookup tables to TypeScript Map interface for each staging input Return structured staging result
AJCC 8th Edition Staging (Prostate) | NCCN Risk Group classification for prostate cancer based on T stage, PSA level, and Gleason score (primary + secondary). | T stage, PSA (ng/mL), Gleason primary + secondary | Risk group: Very Low, Low, Favorable/Unfavorable Intermediate, High, Very High, Metastatic | Decision tree / lookup No LLM / No API call | ajcc_staging_engine.py Lines 265-385 | Port decision tree to TypeScript PSA thresholds: <10, 10-20, >20 Gleason groups: 3+3, 3+4, 4+3, ≥8
AJCC 8th Edition Staging (Lung NSCLC) | TNM-based stage grouping for non-small cell lung cancer. | T, N, M stage values | Stage: IA1-IA3, IB, IIA, IIB, IIIA, IIIB, IIIC, IVA, IVB | Lookup table No LLM / No API call | ajcc_staging_engine.py Lines 390-470 | Port TNM→Stage lookup table Handle all T1-T4, N0-N3, M0-M1 combos
AJCC 8th Edition Staging (Colorectal) | TNM-based stage grouping for colorectal cancer. | T, N, M stage values | Stage: 0, I, IIA, IIB, IIC, IIIA, IIIB, IIIC, IVA, IVB, IVC | Lookup table No LLM / No API call | ajcc_staging_engine.py Lines 475-550 | Port TNM→Stage lookup table Handle Tis, T1-T4, N0-N2, M0-M1
AI Treatment Roadmap Generation | After oncology record creation, makes a SECOND Groq API call to generate comprehensive treatment recommendations based on NCCN guidelines. Fills in surgery, chemo, radiation, immunotherapy, targeted therapy fields. | Cancer type, AJCC stage, histology, grade, tumor size, lymph nodes, biomarkers, AI analysis insights | JSON: { recommended_surgery, recommended_chemotherapy, recommended_radiation, recommended_immunotherapy, recommended_targeted_therapy, treatment_intent, urgency_level } | Groq API (2nd call) NNCN-guideline-aware prompt | data_population_service.py Lines 370-495 | Port roadmap generation prompt Save to OncologyRecord fields Set roadmap_generated_at timestamp Dedicated endpoint to view roadmap
Stage-Specific Recommendations | Generates stage-specific and cancer-type-specific recommendations after AJCC staging. E.g., Stage IV → urgent systemic therapy; breast → BRCA testing. | AJCC stage + cancer type | Array of recommendation strings added to insights/recommendations | Rule-based / deterministic No LLM call | ai_analysis_service.py Lines 1180-1239 | Port recommendation rules to TypeScript Stage IV/III/II rules Cancer-specific rules (BRCA, PSA, etc.)
AUTO-POPULATION FLOWS
Auto Oncology Record from Pathology | When a pathology report finishes AI analysis, automatically creates an OncologyRecord with extracted data. Sets confirmed_by='ai', diagnosis_confirmed=false (requires doctor approval). | AI-analyzed pathology report with oncology_data containing recognized cancer_type | New OncologyRecord linked to pathology report + Treatment roadmap (via AI) | Business logic + Groq API (for roadmap generation) | data_population_service.py Lines 218-370 | Port auto-creation logic Map cancer types Require doctor confirmation Trigger roadmap generation
Auto Patient Record Population | On report approval, auto-populates patient's Vitals, Medications, Allergies, ChronicConditions from AI-extracted data. All records tagged with data_source='automated' and linked to source report. | Approved MedicalReport with extracted_data | New Vitals, Medication, Allergy, ChronicCondition records (data_source='automated') | Business logic No AI call — uses previously extracted data | data_population_service.py Lines 30-215 | Port population logic Duplicate detection Set data_source='automated' Set source_report FK
PROCESSING INFRASTRUCTURE
Processing Progress Tracker | Tracks document processing through stages with real-time progress: initializing → extracting_text → running_ocr → chunking → ai_analysis → merging_results → staging → complete/failed | Processing events from each pipeline stage | ProcessingProgress entity: current_step, total_steps, percentage, current_page, current_chunk, status | Database entity + WebSocket/SSE | ProcessingProgress model Progress tracker service | ProcessingProgress entity Progress service with event emitter SSE endpoint or WebSocket gateway React progress bar component
Document Complexity Analyzer | Estimates processing difficulty/time based on page count, file size, OCR quality, document type, text density. Used for queue prioritization and user time estimates. | Document metadata: page_count, file_size, is_scanned, document_type | Complexity score Estimated processing time | Heuristic scoring No AI call | document_complexity_analyzer.py | Port scoring heuristics Use for BullMQ priority Show estimated time in UI

## 4. AI Tech Stack
Layer | Django (Current) | NestJS (Target) | NPM Package | Purpose | Notes
LLM API
LLM Provider | Groq Cloud API | Groq Cloud API (same) | groq-sdk | LLM inference for medical text analysis | Same API key works for both
LLM Model | llama-3.3-70b-versatile | llama-3.3-70b-versatile (same) | — | 70B parameter model for medical extraction | Best quality/speed ratio on Groq
LLM Config | temp=0.1, max_tokens=1500 | temp=0.1, max_tokens=1500 (same) | — | Low temperature for deterministic extraction | JSON response_format enforced
Token Chunking | 6000 token chunks, 200 overlap | 6000 token chunks, 200 overlap (same) | — | Handle documents exceeding context window | Character/4 approximation for token count
OCR & PDF
PDF Text Extraction | pdfplumber 0.10.3 | pdf-parse / pdfjs-dist | pdf-parse | Extract text from born-digital PDFs | pdf-parse is simpler; pdfjs-dist more flexible
PDF to Image | pdf2image 1.16.3 + Poppler | pdf-poppler / pdf2pic | pdf-poppler or pdf2pic | Convert PDF pages to images for OCR | Requires Poppler system binary installed
OCR Engine | pytesseract 0.3.10 + Tesseract | node-tesseract-ocr / tesseract.js | node-tesseract-ocr | Extract text from images/scanned docs | node-tesseract-ocr = native Tesseract (faster) tesseract.js = WASM (no system dep, slower)
Image Processing | Pillow 10.1.0 | sharp | sharp | Image preprocessing: grayscale, contrast, sharpen, resize | sharp is the Node standard for image processing
SYSTEM DEPENDENCIES (must install on server)
Tesseract OCR | tesseract-ocr (apt install) | tesseract-ocr (same) | — | OCR engine binary | apt install tesseract-ocr tesseract-ocr-eng
Poppler Utils | poppler-utils (apt install) | poppler-utils (same) | — | PDF rendering tools (pdftoppm) | apt install poppler-utils
libvips | N/A | Required by sharp | — | Image processing library | Usually auto-installed with sharp npm package
QUEUE & PROCESSING
Job Queue | Synchronous (in-request) | BullMQ (Redis-backed) | @nestjs/bullmq, bullmq | Async background processing for document pipeline | Allows concurrent processing, retries, priority
Redis | Not used in Django AI | Required for BullMQ | ioredis | Queue backend + caching | Already in tech stack for sessions
Progress Tracking | ProcessingProgress model | ProcessingProgress entity + SSE/WS | @nestjs/event-emitter | Real-time processing progress updates | Server-Sent Events or WebSocket Gateway
DETERMINISTIC ENGINES (no external deps)
AJCC Staging | ajcc_staging_engine.py (581 lines) | ajcc-staging.service.ts | — | Cancer staging lookup tables | Pure TypeScript — no dependencies
Lab Abnormal Detection | ai_analysis_service.py L264-291 | lab-detection.service.ts | — | Reference range parsing + flagging | Pure TypeScript — no dependencies
Report Type Detection | ai_analysis_service.py L310-370 | report-classifier.service.ts | — | Keyword-based document classification | Pure TypeScript — no dependencies
Stage Recommendations | ai_analysis_service.py L1180-1239 | staging-recommendations.service.ts | — | Stage-specific treatment recommendations | Pure TypeScript — no dependencies
DOCKER IMAGE ADDITIONS
Dockerfile additions | N/A | Add to NestJS Dockerfile: | —
|  | RUN apt-get update && apt-get install -y \ | — | Install system deps in Docker
|  | tesseract-ocr tesseract-ocr-eng \ | — | Tesseract + English language pack
|  | poppler-utils \ | — | PDF tools (pdftoppm, pdfinfo)
|  | && rm -rf /var/lib/apt/lists/* | — | Clean apt cache

## 5. Roles & Permissions
Module / Feature | SuperAdmin | Hospital Admin | Doctor | Nurse | Chemist / Pharmacist | Patient
— USER MANAGEMENT —
Create/Edit Hospital | Full | — | — | — | — | —
Create/Edit Users (Doctors, Nurses) | Full | Full | — | — | — | —
Assign Roles & Permissions | Full | Limited | — | — | — | —
View All Users Across Hospitals | Full | — | — | — | — | —
Manage Own Profile | Full | Full | Full | Full | Full | Full
— PATIENT MANAGEMENT —
Register New Patient | Full | Full | Full | Full | — | —
View Patient List | Full | Full | Full | Full | Limited | Own Only
Edit Patient Demographics | Full | Full | Full | Limited | — | Own Only
View Patient Medical History | Full | Full | Full | Full | Limited | Own Only
Manage Emergency Contacts | Full | Full | Full | Full | — | Own Only
Upload/View Documents | Full | Full | Full | Full | Limited | Own Only
— AI DOCUMENT ANALYSIS —
Upload Medical Reports for AI Analysis | Full | Full | Full | Full | — | —
View AI Processing Progress | Full | Full | Full | Full | — | —
View AI Extracted Data & Insights | Full | Full | Full | Full | Limited | Own Only
Approve AI Analysis (populate records) | Full | Full | Full | — | — | —
Retry Failed AI Processing | Full | Full | Full | — | — | —
View AI Treatment Roadmap | Full | Full | Full | Full | View | Own Only
Confirm AI-Created Oncology Record | — | — | Full | — | — | —
View AI Confidence Scores | Full | Full | Full | Full | — | —
AI Analysis Audit Trail | Full | Full | — | — | — | —
— ONCOLOGY / CANCER MODULES —
Create Cancer Diagnosis Record | — | — | Full | — | — | —
Edit Diagnosis Details | Full | — | Full | — | — | —
View Diagnosis Details | Full | Full | Full | Full | View | Own Only
Assign Chemo Protocol | — | — | Full | — | — | —
View Treatment Plan | Full | Full | Full | Full | Full | Own Only
View AJCC Staging Results | Full | Full | Full | Full | View | Own Only
— CHEMOTHERAPY TRACKING —
Schedule Chemo Sessions | — | — | Full | Full | — | —
Mark Session Complete | — | — | Full | Full | — | —
Log Missed Session | — | — | Full | Full | — | —
View Chemo Calendar | Full | Full | Full | Full | Full | Own Only
View Remaining Sessions Count | Full | Full | Full | Full | Full | Own Only
Pre-Chemo Checklist | — | — | Full | Full | — | —
— MEDICATIONS —
Prescribe Medications | — | — | Full | — | — | —
Verify/Dispense Medications | — | — | — | — | Full | —
View Medication List | Full | Full | Full | Full | Full | Own Only
Log Extra/Emergency Meds | — | — | Full | Full | Full | —
Drug Interaction Alerts | — | — | View | View | Full | —
— NOTIFICATIONS —
Configure Notification Rules | Full | Full | — | — | — | —
Send Manual Notifications | Full | Full | Full | Full | — | —
Receive Treatment Alerts | — | — | Full | Full | Full | Full
Manage Notification Preferences | Full | Full | Full | Full | Full | Full
View Notification History | Full | Full | Own | Own | Own | Own
— BENCHMARKS & ANALYTICS —
View Hospital-Wide Analytics | Full | Full | — | — | — | —
View Patient Benchmarks | Full | Full | Full | Full | — | Own Only
View Tumor Marker Trends | Full | Full | Full | Full | — | Own Only
Compare Hospital vs National | Full | Full | Full | — | — | —
Export Reports | Full | Full | Full | Limited | — | —
— ER & EMERGENCY —
Log ER Visit | — | — | Full | Full | — | —
View ER History | Full | Full | Full | Full | — | Own Only
Log Emergency Medications | — | — | Full | Full | Full | —
ER Trend Analytics | Full | Full | Full | — | — | —
— REPORTS —
Generate Patient Reports | Full | Full | Full | Limited | — | Own Only
Generate Hospital Reports | Full | Full | — | — | — | —
Insurance/Billing Reports | Full | Full | Full | — | — | Own Only
Audit Trail Reports | Full | Full | — | — | — | —

## 6. Cancer Modules Detail
Cancer Type | Diagnosis Fields | Chemo Protocols | Key Tumor Markers | Benchmark Metrics | AI Extraction Focus | AJCC Staging Logic
Breast Cancer | • Tumor Size & Grade • ER/PR Status (+/-) • HER2 Status (+/-) • BRCA1/BRCA2 mutation • Lymph node involvement • TNM Staging (I-IV) • Histology type • Ki-67 index | • AC-T (Adriamycin + Cyclophosphamide → Taxol) • TC (Taxotere + Cyclophosphamide) • TCH (for HER2+) • CMF (Cyclophosphamide + Methotrexate + 5-FU) • Trastuzumab (Herceptin) • Hormone Therapy (Tamoxifen/AI) | • CA 15-3 • CA 27.29 • CEA • HER2/neu levels | • CA 15-3 trend (↑↓) • Tumor size reduction % • Chemo completion rate • Recurrence-free survival • Treatment response (CR/PR/SD/PD) | AI extracts from pathology: • ER/PR/HER2 (IHC scores) • Ki-67 percentage • Tumor size in mm/cm • Lymph node count (+/-) • Grade (Nottingham) • Histology type • TNM staging • BRCA status if noted • Molecular subtype | Anatomic: T+N+M Prognostic: T+N+M+Grade+ER/PR/HER2 Subtypes: • Luminal A (ER+/HER2-/low Ki67) • Luminal B (ER+/HER2-/high Ki67) • HER2+ (HER2+) • Triple-neg (ER-/PR-/HER2-)
Prostate Cancer | • Gleason Score (3+3 to 5+5) • PSA Level (ng/mL) • TNM Staging • Risk Group (Low/Inter/High) • Biopsy results • Digital rectal exam • Bone scan results | • Docetaxel + Prednisone • Cabazitaxel • Mitoxantrone • Abiraterone + Prednisone • Enzalutamide • ADT (LHRH agonists/antagonists) • Radiation combos | • PSA (ng/mL) • PSA Velocity • PSA Doubling Time • Testosterone levels • Alkaline Phosphatase | • PSA trend (↑↓) over time • PSA response (>50% drop) • Time to PSA nadir • Chemo completion rate • Bone metastasis progression | AI extracts from pathology: • Gleason primary + secondary • PSA at diagnosis • Number of +/- cores • Tumor volume % • Perineural invasion • Extraprostatic extension • Seminal vesicle invasion • Margin status | NCCN Risk Groups: • Very Low: T1c, Gleason 3+3, PSA<10, <3 cores+ • Low: T1-T2a, Gleason 3+3, PSA<10 • Intermediate: T2b-T2c or Gleason 3+4/4+3 or PSA 10-20 • High: T3a or Gleason 8+ or PSA>20 • Very High: T3b-T4 or primary Gleason 5 • Metastatic: M1
Lung Cancer | • Type: SCLC vs NSCLC • Subtype (Adeno/Squamous/Large) • Staging (I-IV / Limited-Extensive) • Mutations (EGFR, ALK, ROS1, PD-L1%) • Pulmonary Function Tests • Biopsy/Pathology • Performance Status (ECOG) | • Cisplatin + Etoposide (SCLC) • Carboplatin + Paclitaxel • Carboplatin + Pemetrexed (non-squamous) • Pembrolizumab (immunotherapy) • Atezolizumab + Chemo • Targeted: Osimertinib, Crizotinib • Concurrent chemoradiation | • CYFRA 21-1 • NSE (for SCLC) • CEA • SCC Antigen • PD-L1 expression % | • Tumor marker trends (↑↓) • PFT trend (FEV1, DLCO) • Treatment response (RECIST) • Progression-free survival • Immunotherapy response rate | AI extracts from pathology: • NSCLC vs SCLC classification • EGFR mutation status & type • ALK rearrangement (IHC/FISH) • ROS1 rearrangement • PD-L1 TPS percentage • KRAS G12C status • Histology subtype • TNM staging • Lymph node stations | NSCLC TNM Staging: • IA1-IA3: T1a-c, N0, M0 • IB: T2a, N0, M0 • IIA: T2b, N0, M0 • IIB: T1-2, N1 or T3, N0 • IIIA: T1-2 N2 or T3 N1 or T4 N0-1 • IIIB: T1-2 N3 or T3-4 N2 • IIIC: T3-4, N3 • IVA-IVB: M1a-c
Colorectal Cancer | • Tumor Location (Colon/Rectum/Segment) • TNM Staging (I-IV) • MSI Status (MSI-H/MSS) • KRAS/NRAS/BRAF mutation • Grade (Well/Mod/Poorly diff) • Lymph node count • Colonoscopy findings | • FOLFOX (5-FU + Leucovorin + Oxaliplatin) • FOLFIRI (5-FU + Leucovorin + Irinotecan) • CAPOX (Capecitabine + Oxaliplatin) • Bevacizumab (Avastin) • Cetuximab (for KRAS wild-type) • Pembrolizumab (for MSI-H) • Adjuvant vs Palliative regimens | • CEA (ng/mL) • CA 19-9 • LDH • Microsatellite status | • CEA trend (↑↓) • Treatment response (RECIST) • Chemo completion rate • Neuropathy grade tracking • 5-year survival benchmarks | AI extracts from pathology: • Tumor site (cecum→rectum) • MSI/MMR status (IHC + PCR) • KRAS exon 2/3/4 mutation • NRAS mutation status • BRAF V600E mutation • CEA at diagnosis • Lymph nodes examined vs + • Tumor deposits • Circumferential margin • Lymphovascular invasion | TNM Stage Groups: • 0: Tis, N0, M0 • I: T1-T2, N0, M0 • IIA: T3, N0, M0 • IIB: T4a, N0, M0 • IIC: T4b, N0, M0 • IIIA: T1-2 N1 or T1 N2a • IIIB: T3-4a N1 or T2-3 N2a or T1-2 N2b • IIIC: T4a N2a or T3-4a N2b or T4b N1-2 • IVA: M1a • IVB: M1b • IVC: M1c

## 7. Notification System
# | Trigger Event | Channel | Primary Recipient | Secondary Recipient | Message Summary | Frequency | Priority
1 | Chemo session missed | Email + SMS + Push | Patient | Emergency Contact + Doctor | You missed your chemo session on [date]. Please contact your care team to reschedule immediately. | Immediate + 24hr follow-up | CRITICAL
2 | Chemo session reminder (upcoming) | Email + SMS + Push | Patient | Nurse | Your next chemotherapy session is scheduled for [date] at [time]. Please arrive 30 min early for blood work. | 48hr + 24hr + 2hr before | HIGH
3 | Chemo cycle completed | Email + Push | Patient | Doctor + Nurse | Congratulations! You have completed cycle [X] of [Y]. Your next session is on [date]. | After each cycle | MEDIUM
4 | All chemo cycles completed | Email + SMS | Patient | Doctor + Emergency Contact | Your chemotherapy treatment is complete. Follow-up appointment scheduled for [date]. | Once | HIGH
5 | Doctor unavailable / on leave | Email + SMS | Patient | Hospital Admin + Backup Doctor | Dr. [Name] is unavailable on [date]. Your appointment has been reassigned to Dr. [Backup]. | Immediate | HIGH
6 | Doctor assignment change | Email | Patient | New Doctor + Old Doctor | Your oncologist has been changed to Dr. [Name]. Please contact the clinic for any questions. | Immediate | MEDIUM
7 | Tumor marker rising (above threshold) | Email + Push | Doctor | Nurse | ALERT: Patient [Name]'s [Marker] has increased from [X] to [Y]. Review and assess treatment plan. | Immediate | CRITICAL
8 | Tumor marker improving | Email + Push | Patient | Doctor | Great news! Your [Marker] levels are trending downward. Keep following your treatment plan. | After each result | LOW
9 | Benchmark deviation | Email | Doctor | Hospital Admin | Patient [Name]'s treatment response is below expected benchmarks for [Cancer Type] Stage [X]. | Weekly digest | HIGH
10 | ER visit logged | Email + SMS | Oncologist | Nurse + Hospital Admin | ALERT: Patient [Name] was admitted to ER on [date]. Reason: [Category]. Review medications. | Immediate | CRITICAL
11 | Extra medication administered | Email + Push | Oncologist | Chemist/Pharmacist | Additional medication [Drug] was administered to Patient [Name] during ER visit. Review for interactions. | Immediate | HIGH
12 | Unplanned hospitalization | Email + SMS | Doctor + Nurse | Emergency Contact | Patient [Name] has been hospitalized unexpectedly. Reason: [Details]. Oncology team notified. | Immediate | CRITICAL
13 | AI analysis complete | Email + Push | Doctor | Nurse | AI analysis of [Patient Name]'s [Report Type] is complete. Review extracted data and approve/reject. | Immediate | HIGH
14 | AI detected critical finding | Email + SMS + Push | Oncologist | Hospital Admin | URGENT: AI detected [Stage IV / critical abnormality] in [Patient Name]'s pathology report. Immediate review required. | Immediate | CRITICAL
15 | AI oncology record created (pending confirmation) | Email + Push | Doctor | Nurse | AI has auto-created an oncology record for [Patient Name] from pathology report. Doctor confirmation required. | Immediate | HIGH
16 | AI treatment roadmap generated | Email + Push | Doctor | Patient | AI has generated a treatment roadmap for [Patient Name]. Review recommendations and customize treatment plan. | Immediate | MEDIUM
17 | AI processing failed | Email | Hospital Admin | Doctor | AI processing failed for [Patient Name]'s report: [error]. Please retry or manually enter data. | Immediate | MEDIUM
18 | Lab work / blood test reminder | Email + SMS | Patient | Nurse | Your blood work is due before your next chemo session on [date]. Please visit the lab by [deadline]. | 72hr + 24hr before | MEDIUM
19 | Follow-up scan due | Email + SMS + Push | Patient | Doctor | Your follow-up [scan type] is due. Please schedule your appointment before [date]. | 1 week + 3 days before | MEDIUM
20 | Treatment plan review due | Email | Doctor | Nurse | Patient [Name]'s treatment plan is due for review (last reviewed: [date]). | Monthly or per protocol | MEDIUM
21 | Patient registered / onboarded | Email | Patient | Doctor + Nurse | Welcome to [Hospital] Oncology Care. Your treatment team and portal access details are ready. | Once | LOW
22 | Insurance expiration warning | Email + SMS | Patient | Hospital Admin | Your insurance coverage is expiring on [date]. Please update your insurance information. | 30 days + 7 days before | MEDIUM
23 | Emergency contact not set | Push + Email | Patient | Nurse | Please add an emergency contact to your profile. This is required for your safety during treatment. | Weekly until resolved | HIGH

## 8. Benchmarks & Analytics
Dashboard Section | Metric / KPI | Visualization | Data Source | Update Frequency | Who Sees It | Benchmark Comparison
PATIENT DASHBOARD
Treatment Progress | Chemo cycles completed (X of Y) | Progress bar + counter | Chemo schedule module | After each session | Patient, Doctor, Nurse | Expected vs Actual timeline
Treatment Progress | Days since last treatment | Counter + status badge | Chemo schedule module | Real-time | Patient, Doctor | Protocol-defined interval
Treatment Progress | Next session countdown | Calendar card + timer | Chemo schedule module | Real-time | Patient, Nurse | —
Tumor Markers | Marker value over time | Line chart with trend arrow (↑↓→) | Lab results / AI-extracted | After each lab result | Patient, Doctor | Normal range reference lines
Tumor Markers | Marker change % (since last test) | KPI card with color coding | Lab results / AI-extracted | After each lab result | Patient, Doctor, Nurse | Expected response range
AI Insights | AI confidence score for extraction | Badge (High/Medium/Low) | AI Analysis Service | Per document | Doctor, Admin | —
AI Insights | AI-recommended treatment vs actual | Comparison card | AI roadmap + treatment records | Per record | Doctor | NCCN guideline adherence
Side Effects | Side effect severity score | Radar/spider chart | Patient self-reporting | Weekly | Patient, Doctor, Nurse | Average for same protocol
Medications | Medication adherence % | Gauge chart | Prescription module | Daily | Patient, Nurse, Chemist | Target: >95%
HOSPITAL DASHBOARD
Chemo Operations | Total active patients per cancer type | Donut chart by cancer type | Patient registry | Real-time | SuperAdmin, Hospital Admin | Capacity benchmarks
Chemo Operations | Chemo completion rate % | Bar chart per cancer type | Chemo schedule module | Weekly | Admin, Doctor | National average
Chemo Operations | Missed session rate % | Trend line chart | Chemo schedule module | Weekly | Admin, Doctor, Nurse | Hospital target (<5%)
Chemo Operations | Average delay between cycles (days) | Box plot | Chemo schedule module | Monthly | Admin, Doctor | Protocol-defined intervals
Treatment Outcomes | Treatment response rates (CR/PR/SD/PD) | Stacked bar per cancer type | Oncology assessments | Monthly | Admin, Doctor | Published clinical trial rates
Treatment Outcomes | Recurrence rate % | Trend line per cancer type | Follow-up records | Quarterly | Admin, Doctor | National cancer database
AI Performance | AI extraction accuracy % | KPI card + trend | AI vs manual comparison | Monthly | Admin | Target: >95%
AI Performance | Average document processing time | Bar chart by doc type | Processing progress records | Weekly | Admin | Target: <30 seconds
AI Performance | AI auto-created records confirmed % | Gauge chart | Oncology records audit | Monthly | Admin, Doctor | Target: >90%
ER & Emergency | ER visits per 100 chemo cycles | Bar chart + trend | ER visit logs | Monthly | Admin, Doctor | National oncology ER benchmark
ER & Emergency | Top ER visit reasons | Pie chart / treemap | ER visit logs | Monthly | Admin, Doctor, Nurse | —
ER & Emergency | Unplanned hospitalization rate | KPI card with trend | ER visit logs | Monthly | Admin | CMS benchmark
Financial Metrics | Cost per chemo cycle (avg) | Bar chart per cancer type | Billing module | Monthly | Admin | Regional average
Staff Performance | Patients per oncologist | Bar chart | Assignment records | Real-time | Admin | Recommended ratio

## 9. ER & Emergency Tracking
Category | Field / Feature | Description | Captured By | Visible To | Triggers Notification?
ER VISIT LOGGING
Visit Details | Visit Date & Time | Date/time patient arrived at ER | Nurse / ER Staff | Doctor, Nurse, Admin | Yes — Oncologist notified
Visit Details | ER Facility | Which hospital/ER location | Nurse / ER Staff | Doctor, Admin | No
Visit Details | Reason Category | Dropdown: Fever, Infection, Pain, Chemo Reaction, Bleeding, Breathing Difficulty, Fall, Other | Nurse / ER Staff | Doctor, Nurse, Admin, Patient | Yes — if chemo-related
Visit Details | Detailed Description | Free-text clinical notes about the visit | Doctor / Nurse | Doctor, Nurse | No
Visit Details | Severity Level | Triage: Critical / Urgent / Standard | ER Staff | All Care Team | Yes — if Critical
Visit Details | Outcome | Treated & Released / Admitted / Transferred / Against Medical Advice | Doctor | All Care Team + Admin | Yes — if Admitted
Visit Details | Duration of Stay | Hours in ER / Days if hospitalized | System (calculated) | Doctor, Admin | No
EMERGENCY MEDICATIONS
Extra Meds | Medication Name | Drug administered during ER visit | Doctor / Nurse | Doctor, Nurse, Chemist | Yes — Pharmacist alert
Extra Meds | Dosage & Route | Amount + IV/Oral/IM/SC | Doctor / Nurse | Doctor, Nurse, Chemist | No
Extra Meds | Reason for Extra Med | Why this med was needed (linked to ER reason) | Doctor | Doctor, Chemist | No
Extra Meds | Drug Interaction Check | Auto-check against current chemo + support meds | System (auto) | Doctor, Chemist | Yes — if interaction found
Extra Meds | Impact on Treatment Plan | Chemo delayed / Protocol modified / No change | Doctor | Doctor, Nurse, Admin | Yes — if plan changed
FOLLOW-UP ACTIONS
Follow-up | Post-ER Assessment Required | Flag: Does oncologist need to reassess? | ER Doctor | Oncologist | Yes
Follow-up | Chemo Schedule Impact | Next session: On time / Delayed / Cancelled | Oncologist | Patient, Nurse | Yes — Patient notified
Follow-up | Additional Tests Ordered | Labs, imaging, or consults ordered post-ER | Doctor | Nurse, Patient | Yes — scheduling
Follow-up | Emergency Contact Notified | Was emergency contact called? When? | Nurse | Admin | Auto-logged
ANALYTICS (Dashboard)
Analytics | ER visits per patient (over time) | Track frequency of ER visits per patient | System | Doctor, Admin | —
Analytics | ER visits by cancer type | Compare ER rates across Breast/Prostate/Lung/Colorectal | System | Admin | —
Analytics | Most common ER reasons | Top reasons by category | System | Admin, Doctor | —
Analytics | ER visits post-chemo (within 7 days) | How many ER visits occur shortly after chemo | System | Admin, Doctor | —
Analytics | Extra medication frequency | Most commonly administered emergency drugs | System | Admin, Chemist | —
Analytics | Cost per ER episode | Average cost of ER visits per cancer type | Billing | Admin | —

## 10. Tech Stack
Layer | Technology | Purpose | Notes
Frontend | React 18 + TypeScript | Patient portal & Hospital dashboard SPA | Vite build tool, responsive design
Frontend | Tailwind CSS / Ant Design | UI component library & styling | Consistent medical-grade UI
Frontend | React Query (TanStack) | API state management & caching | Optimistic updates, real-time sync
Frontend | Chart.js / Recharts | Benchmark visualizations & trend charts | Tumor marker graphs, analytics
Frontend | React Router v6 | Client-side routing & role-based routes | Protected routes per role
Backend | NestJS + TypeScript | REST API server & business logic | Modular architecture, guards, interceptors
Backend | TypeORM | Database ORM & migrations | Entity-based models, relations
Backend | PostgreSQL | Primary relational database | HIPAA-compliant data storage
Backend | Redis | Caching, session store, rate limiting, job queue | BullMQ backing for async processing
Backend | JWT + Passport | Authentication & authorization | Role-based guards, refresh tokens
Backend | class-validator + class-transformer | DTO validation layer | Request validation, whitelist, transform
Backend | Winston / Pino | Structured logging | Request logging, error tracking, audit trail
AI / ML | Groq API (Llama 3.3 70B) | LLM-powered medical text analysis | groq-sdk npm package, JSON mode
AI / ML | Tesseract OCR | Text extraction from scanned documents | node-tesseract-ocr + tesseract-ocr system binary
AI / ML | pdf-parse / pdfjs-dist | PDF text extraction (digital PDFs) | Extract text layer from born-digital PDFs
AI / ML | pdf-poppler / pdf2pic | PDF to image conversion | For OCR pipeline on scanned PDFs
AI / ML | sharp | Image preprocessing for OCR | Grayscale, contrast, sharpen, resize
AI / ML | AJCC Staging Engine | Deterministic cancer staging (no AI) | Pure TypeScript lookup tables, AJCC 8th Edition
AI / ML | BullMQ | Async document processing queue | Background processing with retries & priority
Notifications | SendGrid / AWS SES | Email notification delivery | Templates, tracking, compliance
Notifications | Twilio | SMS notification delivery | Patient reminders, emergency alerts
Notifications | Firebase Cloud Messaging | Push notifications | Mobile + browser push
Notifications | BullMQ (Redis) | Async notification processing | Retry logic, scheduled delivery
Infrastructure | Docker + Docker Compose | Containerization | Dev/staging/production parity
Infrastructure | AWS / GCP | Cloud hosting | HIPAA-eligible services
Infrastructure | GitHub Actions | CI/CD pipeline | Automated testing + deployment
Infrastructure | Nginx | Reverse proxy & load balancer | SSL termination, rate limiting
Security | HIPAA Compliance | Healthcare data protection | Encryption at rest + transit, audit logs
Security | RBAC (Role-Based Access) | Permission enforcement | 6 roles with granular permissions
Security | Data Encryption | AES-256 at rest, TLS 1.3 in transit | PHI protection
Security | Audit Logging | Track all data access & changes | Compliance reporting
Testing | Jest | Unit & integration testing | Backend + Frontend
Testing | Cypress / Playwright | End-to-end testing | Critical workflow coverage
Testing | k6 / Artillery | Load & performance testing | Chemo scheduling + AI processing stress tests

## 11. Milestones
# | Milestone | Target Date | Deliverables | Acceptance Criteria | Dependencies | Status
M1 | Infrastructure & DevOps Complete | Week 2 | • .env files for all environments • Docker + docker-compose working • CI/CD pipeline running • Health check endpoint • Logging configured • TypeORM migrations setup | • All team members can run project via docker-compose up • CI builds pass on main branch • Migrations run cleanly • Logs structured and queryable | None — first milestone | Not Started
M2 | DTOs & Validation Complete | Week 4 | • DTOs created for ALL endpoints (30+ DTOs) • class-validator decorators on all fields • Swagger @ApiProperty on all DTOs • Global exception filter • Standardized API response format • File upload infrastructure (Multer + storage) | • Invalid requests return proper 400 errors with field-level messages • Swagger docs show request/response schemas • File uploads working (PDF, images) • API responses follow consistent format | M1 complete | Not Started
M3 | Auth & Role System Complete | Week 6 | • RBAC with 6 roles + guards • Register/Forgot Password/Change Password • Audit logging on all auth events • Session management + token blacklisting • Rate limiting on auth endpoints • User management CRUD | • Each role can only access permitted routes • JWT refresh + rotation working • Admin can CRUD users • Failed logins are rate-limited • Audit trail queryable | M2 complete | Not Started
M4 | Patient Module & First Cancer Module | Week 10 | • Patient registration with validation • Breast cancer diagnosis & chemo tracking • First cancer module fully functional • Patient portal v1 (read-only) | • Doctor can create diagnosis + assign chemo • Patient sees treatment progress • Tumor markers tracked with trends • All inputs validated via DTOs | M3 complete | Not Started
M5 | All 4 Cancer Modules Complete | Week 16 | • Prostate, Lung, Colorectal modules • All chemo protocols implemented • Tumor marker tracking for each • Cancer-specific benchmarks | • All 4 cancer types fully functional • Protocol-specific workflows working • Marker trend charts displaying | M4 complete | Not Started
M6 | AI: OCR & Text Extraction Working | Week 18 | • MedicalReport entity & file upload pipeline • PDF text extraction (digital + scanned) • Image OCR with preprocessing • Text cleanup & artifact removal • Document type auto-detection • Processing progress tracking | • Can upload PDF/image → text extracted • Scanned PDFs OCR'd with >90% accuracy • Document type correctly classified • Progress shown in real-time | M2 (file upload infrastructure) | Not Started
M7 | AI: LLM Analysis & Staging Working | Week 22 | • Groq API integration (direct + chunked mode) • All 6 document-type-specific prompts • Abnormal lab detection • AJCC staging engine (all 4 cancer types) • Stage-specific recommendations • AI confidence scoring | • Medical reports analyzed in <30s • Extracted data matches report content • AJCC staging correct per test suite • Large documents chunked & merged correctly • Abnormal labs flagged | M6 complete | Not Started
M8 | AI: Auto-Population & Treatment Roadmap | Week 24 | • Auto-create OncologyRecord from pathology • Treatment roadmap generation (NCCN-based) • Report approval → patient record population • Data source tracking (manual vs automated) • create-from-report API endpoint • Bulk document processing | • Pathology report → OncologyRecord auto-created • Treatment roadmap has surgery/chemo/radiation/immuno/targeted recs • Approval populates vitals/meds/allergies/conditions • All auto-created records tagged data_source='automated' • Doctor can confirm/edit AI-created records | M7 complete + M5 complete | Not Started
M9 | AI Processing Pipeline (End-to-End) | Week 26 | • Full pipeline: upload → OCR → analyze → stage → populate • BullMQ background processing • WebSocket/SSE progress updates • Error recovery & retry • Queue management • Document complexity estimation | • Complete pipeline runs in background • Frontend shows real-time progress • Failed documents can be retried • Concurrent processing works • Processing time estimated upfront | M8 complete | Not Started
M10 | Chemo Engine & Medications | Week 30 | • Chemo scheduling calendar • Missed session detection • Medication management • Chemist verification flow • Drug interaction alerts | • Sessions auto-schedule per protocol • Missed sessions flagged within 24hr • Drug interactions detected • Chemist can verify/dispense | M5 complete | Not Started
M11 | Notification System Live | Week 32 | • Email + SMS + Push working • All 23 notification triggers active • AI-specific notifications (analysis complete, critical finding, etc.) • Alert rules engine • User preference management | • Missed chemo triggers notification • AI critical finding sends urgent alert • Doctor unavailable alerts patient • AI processing complete notifies doctor | M10 + M9 complete | Not Started
M12 | Dashboards & Patient Portal | Week 36 | • Patient + Hospital dashboards • Tumor marker trend charts • AI performance metrics • ER analytics • Patient portal (treatment journey, AI summary, chemo counter) | • All charts rendering correctly • AI extraction accuracy tracked • Role-based visibility enforced • Patient sees plain-language AI treatment summary | M9 + M10 complete | Not Started
M13 | Reports, Compliance & UAT | Week 38 | • PDF report generation • AI analysis audit trail • Insurance/billing exports • Compliance audit reports | • Reports export correctly as PDF • AI audit logs complete and searchable • HIPAA compliance checklist passed | M12 complete | Not Started
M14 | Testing & Production Launch | Week 42 | • Full QA testing (>80% coverage) • E2E testing including AI pipeline • Security audit & pen testing • AI processing load testing • UAT with hospital staff • Production deployment • Documentation & training | • >80% test coverage • Zero critical bugs • AI processing handles 50+ concurrent docs • Hospital staff trained • System stable under load • Full documentation delivered | M1–M13 complete | Not Started

## 12. Patient Portal Screens
Screen / Page | Key Components | Data Displayed | Actions Available | AI-Powered Features
Dashboard (Home) | • Treatment progress card • Next appointment card • Tumor marker mini-chart • Recent notifications • Quick actions • AI summary card | • Chemo cycles: X of Y completed • Days until next session • Latest marker value with trend • Upcoming lab work dates | • View full schedule • Contact care team • Report symptoms • View notifications | • AI-generated treatment summary (plain language) • AI confidence badge on auto-extracted data • AI-detected trends highlighted
My Treatment Plan | • Cancer type & stage summary • Chemo protocol details • Cycle-by-cycle timeline • Medication list • AI treatment roadmap | • Full treatment protocol • Each cycle: date, drugs, status • Completed ✓ / Upcoming / Missed ✗ • Expected completion date | • Download treatment summary • View cycle details • See medication info | • AI treatment roadmap panel showing recommended surgery/chemo/radiation/immuno • AJCC stage explanation card • Treatment intent (curative/palliative)
Chemo Schedule | • Calendar view (month/week) • Session detail cards • Pre-chemo checklist status • History log | • All scheduled sessions • Session times & locations • Required pre-visit labs • Completed session summaries | • View session details • See pre-chemo requirements • Download schedule | • AI-suggested optimal scheduling • AI-flagged potential conflicts
My Health Metrics | • Tumor marker trend chart • Side effect tracker • Weight/vitals log • Treatment response indicator | • Marker values over time (line chart) • Trend arrows (↑↓→) • Normal range reference • Side effect severity scores | • Log symptoms • Log weight/vitals • View historical data • Download reports | • AI-extracted lab results auto-populated • AI abnormal lab flagging (↑↓ arrows) • AI comparison to expected response curves
My Medications | • Current medication list • Dosage & schedule • Refill status • Side effect info | • Chemo drugs (per cycle) • Supportive medications • Hormone therapy (if applicable) • Last dispensed dates | • View drug information • Request refill • Report side effects | • AI-extracted medications from reports • AI drug interaction warnings • Medications tagged: manual vs AI-extracted
My Documents & Reports | • Lab reports • Imaging reports • Pathology reports • Prescriptions • AI analysis results | • Document list with dates • Document type tags • AI processing status badge • AI extracted summary | • View/download documents • Upload documents • View AI analysis insights | • AI extraction status per document • AI insights panel: key findings • AI recommendations panel • View what AI extracted vs original report
Messages & Communication | • Inbox (care team messages) • Compose new message • Contact directory • Urgent contact info | • Messages from doctor/nurse • Automated system messages • AI processing notifications • Read/unread status | • Reply to messages • New message to care team • Emergency call button | • AI analysis completion notifications • AI-detected urgent finding alerts
My Profile & Settings | • Personal information • Emergency contacts • Insurance details • Notification preferences • Password/security | • Demographics • Emergency contact list • Insurance status & expiry • Notification channel preferences | • Edit profile • Add/edit emergency contacts • Update insurance • Toggle notification channels • Change password | • AI-populated fields highlighted (from report extraction) • Data source indicator: 'Entered by Doctor' vs 'AI-Extracted'

## 13. Gap Analysis
Area | Django (Source) | NestJS (Current State) | Gap | Action Required | Phase
INFRASTRUCTURE
Environment Config | .env with all settings | Hardcoded defaults, no .env file | CRITICAL GAP | Create .env files for all environments | Phase 1
Migrations | Django migrations (30+ files) | TypeORM synchronize:true (no migrations) | CRITICAL GAP | Disable sync, generate initial migration | Phase 1
Docker | N/A (manual deployment) | N/A | NEW — needed for both | Create Dockerfiles + docker-compose | Phase 1
CI/CD | N/A | N/A | NEW — needed for both | Create GitHub Actions workflows | Phase 1
Logging | Django debug logging | No logging configured | GAP | Setup Winston/Pino structured logging | Phase 1
File Uploads | Django media handling | No file upload support | CRITICAL GAP | Configure Multer + storage service | Phase 1
VALIDATION
DTOs | Django REST serializers (full validation) | ZERO DTOs — all endpoints use 'any' type | CRITICAL GAP | Create 30+ DTOs with class-validator | Phase 1
Error Handling | Django REST error formatting | Default NestJS exception handler | GAP | Custom exception filter + response format | Phase 1
Swagger Docs | N/A (DRF browsable API) | Swagger exists but minimal (no schemas) | GAP | Add @ApiProperty to all DTOs | Phase 1
AUTH & RBAC
Authentication | JWT (SimpleJWT) — login + refresh | JWT (Passport) — login + refresh | PARTIAL — same feature set | Enhance: register, forgot password, audit | Phase 2
RBAC | Django admin permissions | No role guards — JWT only (all-or-nothing auth) | CRITICAL GAP | Implement @Roles() decorator + RolesGuard | Phase 2
User Management | Django admin CRUD | Only initial admin auto-seed | GAP | Full user CRUD endpoints per role | Phase 2
AI / ML
MedicalReport Model | Full model (15+ fields, file upload, status pipeline) | NOT PORTED | CRITICAL GAP | Create MedicalReport entity + CRUD + upload | Phase 4
ProcessingProgress Model | Progress tracking (steps, %, status) | NOT PORTED | GAP | Create ProcessingProgress entity | Phase 4
Text Extraction (PDF) | pdfplumber (digital PDFs) | NOT PORTED | CRITICAL GAP | Use pdf-parse npm package | Phase 4
OCR (Scanned PDFs) | pdf2image + pytesseract + PIL preprocessing | NOT PORTED | CRITICAL GAP | Use pdf-poppler + node-tesseract-ocr + sharp | Phase 4
AI Analysis (Groq LLM) | Groq API (Llama 3.3 70B) — 6 prompt types | NOT PORTED | CRITICAL GAP | Use groq-sdk npm, port all 6 prompts | Phase 4
Document Chunking | 6000 token chunks, overlap, merge | NOT PORTED | GAP | Port chunking + merge logic to TypeScript | Phase 4
Report Type Detection | Keyword-based NLP classification | NOT PORTED | GAP | Port keyword dictionaries + matching | Phase 4
Abnormal Lab Detection | Reference range parsing + flagging | NOT PORTED | GAP | Port parsing logic to TypeScript | Phase 4
AJCC Staging Engine | 581 lines — 4 cancer types | NOT PORTED | CRITICAL GAP | Port lookup tables + decision trees | Phase 4
Treatment Roadmap (AI) | 2nd Groq API call for NCCN recommendations | NOT PORTED | CRITICAL GAP | Port roadmap prompt + OncologyRecord fields | Phase 4
Auto Population | Approval → populate vitals/meds/allergies | NOT PORTED | GAP | Port DataPopulationService logic | Phase 4
Auto OncologyRecord | Pathology → auto-create oncology record | NOT PORTED | CRITICAL GAP | Port auto-creation + cancer type mapping | Phase 4
create_from_report API | POST endpoint for processing reports | NOT PORTED | GAP | Create endpoint + pipeline trigger | Phase 4
Background Processing | Synchronous (in-request) | NOT PORTED | IMPROVEMENT | Use BullMQ for async processing | Phase 5
EXISTING FEATURES (Already Ported)
Patient CRUD | Full REST API | Full REST API ✓ | DONE | Add DTOs for validation | Phase 1
Oncology CRUD | Full REST API | Full REST API ✓ | DONE | Add DTOs for validation | Phase 1
Treatments/FollowUps/Symptoms | Partial (missing ViewSets in Django) | Full REST API ✓ (NestJS ahead) | NestJS AHEAD | No action needed | —
Payer Submissions | Partial (missing ViewSet in Django) | Full REST API ✓ (NestJS ahead) | NestJS AHEAD | No action needed | —
ChronicConditions | Partial (missing ViewSet in Django) | Full REST API ✓ (NestJS ahead) | NestJS AHEAD | No action needed | —
Dashboard Stats | Custom admin dashboard | GET /api/dashboard/stats ✓ | DONE | Enhance with AI metrics | Phase 8
13 Entities | 13 Django models | 13 TypeORM entities ✓ (faithful mapping) | DONE | Add MedicalReport + ProcessingProgress | Phase 4